## TOC
Business Case Spreadsheet (Template)
Table of Contents

Introduction
	This workbook is called the Business Case Spreadsheet Template (BCT). Its purpose is to provide the user with a head start in building a thorough financial analysis and justification for a project.
	The BCT was constructed as a result of research and analysis of cross-industry, commercial best practices.
	The delivery of the BCT is part of the Enterprise Integration Toolkit which provides a structured method, guidance and tools to DOD personnel in applying cross-industry, commercial best practices to Commercial Off-The-Shelf (COTS) software application procurement and project implementations per OMB circular A-94.

Overview
	The BCT is a multi-tabbed Excel workbook containing pre-constructed forms for input of all key project estimates, financial analysis, sensitivity analysis and summary charting of results.
	The goal of the BCT is to guide the user through the process of gathering project parameters and financial estimation input, iterating on and refining project estimates, completing a detailed financial analysis, producing summary metrics, and, ultimately, using these results to support a "go"/"no-go" decision for project approval and funding.
	The BCT allows for 3 increasingly precise methods of estimation for each major category of cost or benefit. The three estimation types are High-Level, Parametric & Actual. Many of the detail level tabs have headings for each of these three types of estimation in the left margin.
	Information flow within the BCT generally goes from tabs on the right (detail) to tabs on the left (calculation, aggregation and summarization). Therefore, navigation for user familiarity is recommended to start from left (view results/outcomes at summary level) and proceed to the right (understanding of detailed input & estimations).
	Conventions: Fields to be used for user input are in red text, fields carried forward or referenced by other tabs are bold, calculated fields are in black text.
	Overview instructions are provided below. More detailed, supplemental instructions are provided within each tab on its use.

Per Tab Details
	Cash Flow & ROI Analysis	This tab contains various measures of financial feasibility, Return on Investment (ROI) and justification, including: Net Present Value (NPV), Internal Rate of Return (IRR), and Breakeven. Pulls data mainly from the Cost & Benefit Summary tab. Also pulls a few, key input parameters from Input of Assumptions area of Input Sensitivity tab.
		Also contains the underlying year-to-year estimated financial results, which roll-up into a Cash Flow (CF) analysis containing the following sub-categories: One-time costs (expenses and capital), Ongoing Costs, Ongoing Benefits, Depreciation.
	Input & Tornado Sensitivity Analysis	Location of all key input parameters. Also, provides workspace to run the integrated Tornado macro. This macro takes user-defined input parameters and produces a tornado diagram. This chart allows the user to analyze the relative importance of the input parameters in terms of their influence on the outcome of the BCT model (typically outcome is measured in 5 year NPV). This type of sensitivity analysis is in compliance with OMB circular A-74.
	Cost & Benefit Summary	Summarizes major categories of costs and benefits. Acts as a rudimentary "pivot table" for user selection of level of estimate. As directed by "x" marks from the user, the CostBenefit Summary tab pulls information from the appropriate estimation type area of each supporting, detailed workbook tabs: Savings, Revenue, Incremental Ongoing Costs, Project Expenses & Project Capital.
	Savings Benefit Estimates	Provides a workspace for user quantification of incremental cost savings benefits of a project at three, increasingly accurate/detailed levels of estimation. Pulls key input parameters from Input of Assumptions area of Input Sensitivity tab.
	Revenue Benefit Estimates	Provides a workspace for quantification of incremental revenue generating benefits of a project at three, increasingly accurate/detailed levels of estimation. Pulls key input parameters from Input of Assumptions area of Input Sensitivity tab.
	Sample Benefits Identification Model	Provides an approach to thinking through the potential benefit areas, benefit metrics and benefit calculations associated with a proposed project in a commercial setting. Currently no inbound or outbound links to/from the rest of the Business Case Template.
	Incremental Ongoing Costs	Provides a workspace for user quantification of various, incremental, ongoing costs as a result of implementing the project. This sheet provides for this quantification at three, increasingly accurate/detailed levels of estimation. Pulls key input parameters from Input of Assumptions area of Input Sensitivity tab.
	Project Expenses	Provides a workspace for quantification of project expenses required for project implementation. In IT projects, this typically consists of consulting, integration, programming, related travel & expenses, and computer hardware, network equipment, or software that does not fulfill the rules for availability to depreciate over time. Internal labor costs and associated travel & expenses are also typically counted in this category.
	Project Capital Expenditures	Provides a workspace for quantification of project capital goods required for project implementation. In IT projects this typically consists of computer hardware, network equipment, some custom-developed computer software and some consulting. On occasion, this category might also include other capital items such as buildings, furniture, telecommunications equipment, or building renovations.
	Glossary	Provides a listing of key words or phrases, their definition, and how their used.
	Charts	Provides graphical summaries of financial and other analysis results from the BCT.
	Simulation	Provides workspace where the user may run a separately downloadable Excel add-in to automatically simulate many scenarios of the BCT, with user-specified variance of a parameter to generate an inverse cumulative distribution curve.

Installation
		http://www.kellogg.nwu.edu/faculty/myerson/ftp/addins.htm
	SimTools add-in	The BCT uses an Excel add-in, SimTools, which is available for download at the above URL. SimTools supports Monte Carlo simulation and additional statistical analysis of uncertainty in the cost-benefits model. Click on the above link and follow the instructions for downloading to enable these features.

Instructions
1	Read the Business Case Developers Guide to understand the overall approach to developing a business case.
2	Familiarize yourself with the overall structure of the workbook, the approach used for each tab and its subsequent information flow.
3	Use the Benefits ID tab to identify all savings and revenue benefits of the potential project.
4	Perform ballpark parameter research.
5	Revise benefit scenarios in the Savings and Revenue tabs.
6	Revise Incremental Ongoing Costs, if necessary.
7	Revise Project Expenses and Project Capital tabs as this information becomes available.
8	Revise and proof workbook calculations.
9	Ensure "x" marks are provided in the appropriate column of the CostBenefit Summary tab and point to the most accurate/appropriate section/information in each detailed tab. At this stage, most are likely to be "parametric" estimates.
10	Enter all key input parameters in the Input of Assumptions section of the Input Tornado tab. Then, create references to them from all appropriate, underlying detailed tabs.
11	Run preliminary sensitivity analysis & produce tornado diagram by using the Tornado macro.
	Follow the instructions in the Input Tornado tab and within the macro, itself. NPV is recommend as the best output cell as demonstrated in the sample.
	A new sheet will be created in your workbook. It will contain the new tornado diagram, sorted so that the parameters having the most influence on the output cell (NPV in our sample) are at the top and contain the largest horizontal bars.
12	Identify high impact input parameters by looking at top of tornado (largest bars mean degree of influence).
13	Perform parametric research, prioritizing those parameters that were at the top of the most recent tornado diagram.
14	Refine accuracy of all estimates used as input parameters.
15	Run 2nd sensitivity analysis & produce tornado diagram.
16	Download SimTools and place in appropriate directory
17	Select key parameters and run simulation sensitivity analysis.
18	Produce charts.
19	Utilize results as recommended in the Guide
20	Refresh input parameters as more accurate or reliable estimates or information become available. Repeat steps 16 -19 as necessary.
21	After project is implemented and operations are expected to be enjoying the estimated benefits, capture actual Key Performance Indicator (KPI) data.
22	Utilize the information gathered in the step above as Actual Results-level input parameters. Ensure "x" marks in in the appropriate columns in CostBenefit Summary tab. Perform calculations of actual project ROI & summarize/chart results for use in executive presentation.

Troubleshooting
	Immediately upon opening the BCT, click on the Enable Macros button to allow the proper operation of the Tornado diagramming macro for sensitivity analysis.
	If you don't see the Tornado macro under the Tools\Macros sub-menu, your instance of Excel has been configured to disable macros. Please consult with your helpdesk to have macros enabled.
	If the user is attempting to build a reference to a cell within Project Capital or Inctl Ongoing Costs and the typical Excel cursor turns into a hand, preventing specific cell reference, type in the cell location instead.

EITK0304

## Charts
Business Case Spreadsheet (Template)
	Charts

	1	Summary Cash Flow

	Note that this single chart incorporates all significant cash flow measures. For some presentations it may be advisable to produce multiple, simpler charts.

## Simulation
Business Case Spreadsheet (Template)
	Simulation Sensitivity Analysis
	Step #	Sensitivity Simulation Instructions
	1	Generate a tornado diagram following steps in Tornado Diagram section of Input Tornado tab. Identify top influencial parameters.
	2	Plug the following formula into the best estimate cell for a key parameter of the Input Sensitivity tab:					=NORMINV(RAND(),0.15,0.1)				SimTable	2 827 104
			Where NORMINV is the function that best approximates the shape of the distribution for this parameter.					-	4 848 427
			Where the mean of the distribution is 15% and the standard deviation is 10%.					0,01	4 624 103
			Where RAND() is used to generate random numbers between 0 and 1					0,02	4 612 879
			Where the NORMINV function uses this random number to genarate simulations of outcomes (typically NPV in cell D4) for this key parameter as it varies.					0,03	4 471 450
	3	Run SimTable by using the Tools, SimTool, SimTable menu command from within the BCT					0,04	4 386 063
	4	Follow on screen instructions, using 2 columns and approx. 100 rows, starting from cell C4					0,05	4 342 398
	5	Sort cells D5 to end in descending order.					0,06	4 308 955
	6	Use Chart Wizard to plot a line graph as above.					0,07	4 236 063
	7	Observe line graph "tilt": the more horizontal the majority of the curve, the more predictable outcome (NPV) is as the key parameter varies according to the shape of the selected distribution curve.					0,08	4 163 292
	8	Refine the chart for use in summary presentations					0,09	4 154 672
	9	If warranted, the user can perform this process for another, key parameter: to isolate the results of each simulation, start by re-keying a "hard-coded" (not formula, not reference) input of the parameter first chosen in step 2. Then go to step 1, select a new parameter and repeat steps 2 on.					0,10	4 141 343
	10	A more sophisticated and thorough variation on step 9 above is to run a simulation on multiple, key parameters simultaneously. To do this, the user would execute step 2 for select parameters (ex: top 5).					0,10	3 890 804
	*	Keep in mind that after the first time Simulation is run according to the steps above, the model outcome (NPV) will change each and every time the user causes the workbook to re-calculate. Therefore, the BCT will not be re-usable for reliable ROI metrics until all parameters in the Input Sensitivity tab are again "hard-coded."					Simulation of NPV Outcomes Varying % of Improvement in Volume Discount Across an Inverse Normal Distribution					0,11	3 849 653
					0,12	3 847 363
					0,13	3 830 130
					0,14	3 796 984
					0,15	3 699 370
					0,16	3 672 467
					0,17	3 655 058
					0,18	3 653 406
					0,19	3 626 882
					0,20	3 612 798
					0,21	3 605 705
					0,22	3 564 601
					0,23	3 550 219
					0,24	3 539 751
					0,25	3 501 442
					0,26	3 464 060
					0,27	3 441 046
					0,28	3 430 238
					0,29	3 424 279
					0,30	3 392 533
					0,30	3 385 023
					0,31	3 382 496
					0,32	3 368 388
					0,33	3 359 593
					0,34	3 306 677
					0,35	3 266 342
					0,36	3 260 896
					0,37	3 229 145
					0,38	3 224 799
					0,39	3 213 384
					0,40	3 169 014
					0,41	3 164 747
					0,42	3 083 418
					0,43	3 072 923
					0,44	3 042 764
					0,45	3 023 623
					0,46	3 002 392
					0,47	2 978 921
					0,48	2 947 755
					0,49	2 932 449
					0,50	2 927 528
					0,50	2 912 311
					0,51	2 901 903
					0,52	2 889 888
					0,53	2 863 822
					0,54	2 762 266
					0,55	2 745 466
					0,56	2 732 126
					0,57	2 714 991
					0,58	2 694 167
					0,59	2 677 937
					0,60	2 675 544
					0,61	2 665 880
					0,62	2 607 530
					0,63	2 574 002
					0,64	2 569 703
					0,65	2 560 358
					0,66	2 557 159
					0,67	2 550 943
					0,68	2 524 306
					0,69	2 503 759
					0,70	2 499 991
					0,70	2 495 008
					0,71	2 473 317
					0,72	2 454 737
					0,73	2 439 021
					0,74	2 433 409
					0,75	2 412 896
					0,76	2 229 631
					0,77	2 180 936
					0,78	2 169 762
					0,79	2 115 829
					0,80	2 089 109
					0,81	2 039 118
					0,82	1 858 778
					0,83	1 801 783
					0,84	1 742 721
					0,85	1 652 207
					0,86	1 606 657
					0,87	1 583 796
					0,88	1 536 685
					0,89	1 528 045
					0,90	1 511 110
					0,90	1 485 300
					0,91	1 468 015
					0,92	1 415 822
					0,93	1 155 584
					0,94	1 123 376
					0,95	1 045 213
					0,96	972 599
					0,97	874 691
					0,98	608 704
					0,99	590 404
					1,00	388 465

## Input Tornado
Business Case Spreadsheet (Template)
	Input & Tornado Sensitivity Analysis
	1. Ensure all key input parameters are "hard coded" (typed in, not calculated or referenced) into the section below. Start with column D. The user may have to point key cells of the many detailed cost and benefits tabs to these cells in this tab. These "pointer" cells in the detail tabs are colored black in this BCT sample to show that they are not input cells. Also within the table below, provide Minimum (column F) and Maximum (column G) data points for the Best Estimate of Input parameter provided in column D.

	Input of Assumptions		(Assumptions)
	Tab Name	Section Name	Best Estimate Parameter	Name of Parameter	Low Estimate of Parameter	High Estimate of Parameter
	ROI and CF Analysis	Assumptions Per Year	15,00%	Discount Rate	10%	25%
	ROI and CF Analysis	Assumptions Per Year	2,5%	Annual Cost Increases	0%	7%
	ROI and CF Analysis	Assumptions Per Year	2,5%	Annual Benefit Increases	0%	7%
	ROI and CF Analysis	Assumptions Per Year	42%	Corporate Tax Rate	35%	49%
	ROI and CF Analysis	Depreciation & Interest Schedule	8,5%	Interest Rate	6%	12%
	Savings	Purchasing	10%	Est. % improvement in Purchasing productivity	0%	25%
	Savings	Purchasing	10%	Est. incremental % of comparable products identified	5%	15%
	Savings	Purchasing	10%	Est. % improvement in price per P.O.	7%	15%
	Savings	Purchasing	10%	Est. incremental % of same vendor/same month orders	4%	18%
	Savings	Purchasing	15%	Est. % improvement in volume discount	5%	40%
	Savings	Maintenance & Repair	10%	Est. improvement in Maintenance & Repair worker productivity	5%	15%
	Savings	Warehousing/Inventory	10%	Est. avg. reduction in # parts per warehouse	7%	13%
	Savings	Logistics, et al.	10%	Est. improvement in Logistics worker productivity	5%	15%
	Savings	Logistics, et al.	20%	Est. avg. reduction in cost per work order	10%	30%
	Savings	Logistics, et al.	25%	Estimated reduction in premium freight shipments	0%	30%
	Savings	Customer Service	10%	Est. avg improvement in C.S. & O.M. worker productivity	5%	15%
	Savings	Customer Service	50%	Est. % reduction of incorrect orders	35%	60%
	Savings	Customer Service	50%	Est. % reduction in complaint calls	10%	70%
	Savings	IS	3	Est. # decomissioned systems	2	4
	Savings	Finance	10%	Est. avg improvement in Finance worker productivity	5%	15%
	Savings	HR	10%	Est. avg improvement in HR worker productivity	5%	15%
	Revenue	Sales	5%	Est. % increase in price per order	2%	10%
		Sales	10%	Est. % improvement in close rate	0%	20%
		Sales	10%	Est. % decrease in order processing time	3%	13%
		Sales	10%	Est. % improvement in sales travel efficiency	0%	25%
		Sales	10%	Est avg annual reduction in customer loss	5%	15%
		Customer Service	10%	Est. % improvement in customer satisfaction	2%	14%
		Customer Service	10%	Est. incremental % of leads passed per C.S. worker	5%	30%
	Benefits ID
	Ongoing Costs
	Project Expenses
	Project Capital

	2. From the Tools menu, select Macros, highlight TORNADO and click on the "Run" button. Then, follow the pop-up instructions provided by the macro itself. The resulting chart will appear within a newly inserted tab (Sheet 1) in this workbook.

	Tornado Sensitivity Analysis		5 Year NPV	2 827 104

	Savings Sensitivity Analysis Outputs

	Parameters:	Output D48 with low value from F4:F24 for parameter in D4:D24	Output D48 with high value from G4:G24 for parameter in D4:D24	Output Differences:
	Est. % improvement in volume discount	1 614 270	5 069 681	3 455 411
	Est. incremental % of same vendor/same month orders	1 712 996	3 786 243	2 073 246
	Discount Rate	3 245 260	1 624 707	1 620 553
	Est. incremental % of comparable products identified	2 094 042	3 109 019	1 014 977
	Est. % improvement in price per P.O.	2 297 037	3 109 019	811 982
	Corporate Tax Rate	2 986 293	2 216 767	769 526
	Annual Cost Increases	2 478 708	2 835 470	356 762
	Est. % improvement in Purchasing productivity	2 520 332	2 723 328	202 995
	Est. # decomissioned systems	2 520 332	2 682 728	162 396
	Est. % reduction in complaint calls	2 500 033	2 652 279	152 247
	Est. avg. reduction in # parts per warehouse	2 530 711	2 672 349	141 638
	Est. avg. reduction in cost per work order	2 551 938	2 651 123	99 186
	Est. improvement in Maintenance & Repair worker productivity	2 560 931	2 642 129	81 198
	Est. improvement in Logistics worker productivity	2 560 931	2 642 129	81 198
	Est. avg improvement in C.S. & O.M. worker productivity	2 560 931	2 642 129	81 198
	Est. avg improvement in Finance worker productivity	2 560 931	2 642 129	81 198
	Est. avg improvement in HR worker productivity	2 560 931	2 642 129	81 198
	Estimated reduction in premium freight shipments	2 576 156	2 606 605	30 449
	Est. % reduction of incorrect orders	2 584 448	2 612 918	28 470
	Annual Benefit Increases	2 601 530	2 601 530	0
	Interest Rate	2 601 530	2 601 530	0

	Key Savings Parameters

	Revenue Sensitivity Analysis Outputs		5 Year NPV	2 827 104

	Parameters:	Output D46 with low value from F28:F34 for parameter in D28:D34	Output D46 with high value from G28:G34 for parameter in D28:D34	Output Differences:
	Est. % improvement in close rate	2 505 863	2 975 924	470 061
	Est. % improvement in sales travel efficiency	2 598 236	2 984 093	385 857
	Est. % increase in price per order	2 624 439	2 960 811	336 372
	Est. % decrease in order processing time	2 635 471	2 788 590	153 119
	Est. incremental % of leads passed per C.S. worker	2 727 748	2 819 661	91 912
	Est avg annual reduction in customer loss	2 733 408	2 748 379	14 971
	Est. % improvement in customer satisfaction	2 740 894	2 740 894	0

	Key Revenue Parameters

## CF & ROI Analysis
Business Case Spreadsheet (Template)
	Cash Flow & ROI Analysis				5 Year NPV			$2 827 104
					5 Year IRR			60%
					Payback (Yrs.)			1,6
	Project Name:	Generic IT Project
	Project #:

	ASSUMPTIONS PER YEAR	Yr 0	Yr 1	Yr 2	Yr 3	Yr 4	Yr 5	Yr 6	Yr 7	Yr 8	Yr 9	Yr 10		Total

	Assumptions
	Discount Rate	15%
	Annual Cost Increases		0%	2,5%	2,5%	2,5%	2,5%	2,5%	2,5%	2,5%	2,5%	2,5%
	Annual Benefit Increases		0%	2,5%	2,5%	2,5%	2,5%	2,5%	2,5%	2,5%	2,5%	2,5%
	Corporate Tax Rate		42%	42%	42%	42%	42%	42%	42%	42%	42%	42%

	ONE TIME PROJECT COSTS	Yr 0	Yr 1	Yr 2	Yr 3	Yr 4	Yr 5	Yr 6	Yr 7	Yr 8	Yr 9	Yr 10		Total

	Capital Outlays	(show as negative numbers)
	External Consulting Fees	0					0
	Computer & Other Equipment	-1 659 619					-1 659 619
	Asset Category 3	0					0
	Asset Category 4	0					0
	Asset Category 5	0					0
	Sub-Total Capital Outlay	-1 659 619	0	0	0	0	0	0	0	0	0	0		-1 659 619

	One Time Expenses
	External Consulting Fees	-621 575					-621 575
	Internal Personnel Costs	-582 981					-582 981
	IT Installation Costs	0					0
	Sub-Total One Time Expenses	-1 204 556	0	0	0	0	0	0	0	0	0	0		-1 204 556

	Total Outlays	-2 864 175	0	0	0	0	0	0	0	0	0	0		-2 864 175

	EARNINGS IMPACT

		Yr 0	Yr 1	Yr 2	Yr 3	Yr 4	Yr 5	Yr 6	Yr 7	Yr 8	Yr 9	Yr 10		Total
	Projected Costs	(show as negative numbers)
	Depreciation		-331 924	-331 924	-331 924	-331 924	-331 924	0	0	0	0	0		-1 659 619
	On-going costs		-1 240 720	-874 016	-670 740	-571 778	-531 886					-3 889 141
	One Time Expenses	-1 204 556	0	0	0	0	0	0	0	0	0	0		-1 204 556

	Total Costs	-1 204 556	-1 572 644	-1 205 940	-1 002 664	-903 702	-863 810	0	0	0	0	0		-6 753 316

	Projected Benefits
	Additional on-going benefits		1 908 801	1 344 640	1 031 907	879 659	818 287					5 983 294
	Incremental contribution/profits		1 918 201	1 966 156	2 015 310	2 008 025	2 039 475					9 947 167
	Total Benefits		3 827 002	3 310 796	3 047 217	2 887 684	2 857 762	0	0	0	0	0		5 983 294

	Net Projected Impact	-1 204 556	2 254 357	2 104 856	2 044 554	1 983 982	1 993 952	0	0	0	0	0		-770 022

	Tax	505 914	-946 830	-884 040	-858 713	-833 272	-837 460	0	0	0	0	0		-4 360 314
	Income After Tax	-698 642	1 307 527	1 220 817	1 185 841	1 150 709	1 156 492	0	0	0	0	0		-5 130 337

	CASH FLOW	Yr 0	Yr 1	Yr 2	Yr 3	Yr 4	Yr 5	Yr 6	Yr 7	Yr 8	Yr 9	Yr 10		Total

	Capital Outlay	-1 659 619	0	0	0	0	0	0	0	0	0	0		-1 659 619
	One-time Exp. (after tax)	-698 642	0	0	0	0	0	0	0	0		-698 642
	Income After Tax		1 307 527	1 220 817	1 185 841	1 150 709	1 156 492	0	0	0	0	0		6 021 386
	Depreciation		331 924	331 924	331 924	331 924	331 924	0	0	0	0	0		1 659 619
	Net Cash Flow	-2 358 261	1 639 451	1 552 740	1 517 765	1 482 633	1 488 416	0	0	0	0	0		5 322 744

	Discounted Cash Flows	(2 358 261)	1 425 610	1 174 095	997 955	847 700	740 006	-	-	-	-	-
	Cumulative Discounted	(2 358 261)	(932 652)	241 443	1 239 398	2 087 098	2 827 104	2 827 104	2 827 104	2 827 104	2 827 104	2 827 104
	Cumulative Nominal	(2 358 261)	(718 810)	833 930	2 351 695	3 834 328	5 322 744	5 322 744	5 322 744	5 322 744	5 322 744	5 322 744
		0	1	2	3	4	5	6	7	8	9	10

	DEPRECIATION AND INTEREST SCHEDULE

	Beginning Balance	Close	Yr 1	Yr 2	Yr 3	Yr 4	Yr 5	Yr 6	Yr 7	Yr 8	Yr 9	Yr 10		Total
	External Consulting Fees	0	0	0	0	0	0	0	0	0	0	0
	Computer & Other Equipment	1 659 619	1 659 619	1 327 695	995 771	663 848	331 924	0	0	0	0	0
	Asset Category 3	0	0	0	0	0	0	0	0	0	0	0
	Asset Category 4	0	0	0	0	0	0	0	0	0	0	0
	Asset Category 5	0	0	0	0	0	0	0	0	0	0	0
	Total Outlay	1 659 619	1 659 619	1 327 695	995 771	663 848	331 924	0	0	0	0	0

	Depreciation	Life (# of years)
	External Consulting Fees	3	0	0	0	0	0	0	0	0	0	0		0
	Computer & Other Equipment	5	331 924	331 924	331 924	331 924	331 924	0	0	0	0	0		1 659 619
	Asset Category 3	3	0	0	0	0	0	0	0	0	0	0		0
	Asset Category 4	5	0	0	0	0	0	0	0	0	0	0		0
	Asset Category 5	10	0	0	0	0	0	0	0	0	0	0		0
	Total Outlay		331 924	331 924	331 924	331 924	331 924	0	0	0	0	0		1 659 619

	Ending Balance
	External Consulting Fees	0	0	0	0	0	0	0	0	0	0	0
	Computer & Other Equipment	1 659 619	1 327 695	995 771	663 848	331 924	0	0	0	0	0	0
	Asset Category 3	0	0	0	0	0	0	0	0	0	0	0
	Asset Category 4	0	0	0	0	0	0	0	0	0	0	0
	Asset Category 5	0	0	0	0	0	0	0	0	0	0	0
	Total Outlay	1 659 619	1 327 695	995 771	663 848	331 924	0	0	0	0	0	0

	Interest on Avg Balance		126 961	98 747	70 534	42 320	14 107	0	0	0	0	0		352 669
	Interest Rate	8,5%

## CostBenefit Summary
Business Case Spreadsheet (Template)
	Cost & Benefit Summary					Generic IT Project
		Level of Estimation*
			All rows must have an "x" in only one of the three columns below.
		1	2	3		Year 0	Year 1	Year 2	Year 3	Year 4	Year 5	Avg.
	- BENEFITS -
	Incremental Revenue		x			$-	$1 908 801	$1 344 640	$1 031 907	$879 659	$818 287
	Incremental Cost Savings		x			$-	$1 918 201	$1 966 156	$2 015 310	$2 008 025	$2 039 475
	- COSTS -
	Incremental Commissions & Cost of Sales	x				$-	$286 320	$201 696	$154 786	$131 949	$122 743
	Incremental Cost of Operations	x				$-	$763 520	$537 856	$412 763	$351 864	$327 315
	Incremental SG&A Cost	x				$-	$190 880	$134 464	$103 191	$87 966	$81 829
	External Project Expenses (Fees & Other Expenses)		x			$621 575	$-	$-	$-	$-	$-
	Internal Project Expenses (Personnel & Other Expenses)		x			$582 981	$-	$-	$-	$-	$-

	Gross Benefit					$(1 204 556)	$2 586 281	$2 436 780	$2 376 477	$2 315 905	$2 325 876	$2 408 264
	Cumulative Gross Benefit					$(1 204 556)	$1 381 725	$3 818 505	$6 194 983	$8 510 888	$10 836 764

	* Level of Estimation Footnotes:
	1 - High level ("ballpark") estimates are typically based on preliminary research on similar projects, RFI responses and/or non-binding estimates.
	2 - Parametric estimates are typically based on in-depth research, RFP response and/or documented contractual obligation.
	3 - Actual costs and benefits as measured post-implementation for validation.

## Project Capital
Business Case Spreadsheet (Template)
	Project Capital Expenditures

	Level 1 - High Level Estimates			Year 0	Year 1	Year 2	Year 3	Year 4	Year 5
			Total CapEx	$-	$-	$-	$-	$-	$-
	Buildout
	PCs
	Servers
	Network Components
	Application Software License
	OS/DB/Utilities Software License
	Premise-base Telecom Equip.
	Other Infrastructure

	Level 2 - Parametric Estimates	(Sample) Project Capital Expenditures For a New Call Center

	Number of sites required			Year 0	Year 1	Year 2	Year 3	Year 4	Year 5
	1,00		Total CapEx	$1 659 619	$-	$-	$-	$-	$-

	Variables			CapEx Per Site
	Agent Stations	175		$1 659 619
	Non-Agent Stations	75
	Sq. Ft. (120 per seat)	30000		CapEx Cost/Seat
				$9 484

	One Time CapEx Costs	Unit Cost	Quantity	Total

	Buildout	$6 000	30	$180 000	LAN Sub-Total
	LAN Server (Novell)	$6 739	1	$6 739		$539 254
	Front end Cisco Router	$10 000	2	$20 000
	100Mb Fault tolerance Transceiver	$4 500	1	$4 500	Voice Sub-Total
	Accelar Backbone switch	$35 000	2	$70 000		$279 865
	Cisco Switch (24 port)	$2 500	9	$22 500
	LAN Tape backup	$3 400	1	$3 400	Brick and Mortar Sub-Total
	Tapes	$20	40	$800		$840 500
	LAN Management workstations	$3 000	1	$3 000
	Sniffer Network probe	$17 000	1	$17 000
	HP Laser jet 4000	$1 500	1	$1 500
	Fax server	$4 800	1	$4 800
	PC Workstation	$1 000	250	$250 000
	Surge protectors for PC's	$14	250	$3 500
	Equipment racks	$300	1	$300
	Tools, Tywraps, Labels	$500	1	$500
	Novel 4.11 OS	$40	250	$10 000
	Novell Gateway Sessions	$50	25	$1 250	10%
	Managewise LAN software	$10 000	1	$10 000
	HP Openview	$18 000	1	$18 000
	Optivity Switch management software	$10 000	1	$10 000
	Cisco works	$18 000	1	$18 000
	Remote access software	$1 000	1	$1 000
	Attachmate for Windows	$360	25	$9 000	10%
	E-mail software	$71	250	$17 750
	MSOffice	$500	1	$500
	Communications line frame	$3 000	1	$3 000
	Modems FRADS	$500	1	$500
	Training equipment	$5 000	1	$5 000
	SUN Sparc 250 IWS Intranet server	$16 865	1	$16 865
	Intel based intranet server	$4 000	1	$4 000
	Wiznet gateway	$2 400	1	$2 400
	SUN Backup unit	$2 200	1	$2 200
	IWS Backup tapes	$20	40	$800
	Solaris License	$150	3	$450
	SUN Sparc 250 IWS Intranet server	$16 865	1	$16 865
	Lucent PBX	$-	1	$-	Cost per station
	Installation			$-	2000
	Paraphonics IVR	$150 000	1	$150 000
	Genesis CTI Server	$20 000	1	$20 000
	Open Client Sybase License	$31 000	3	$93 000
	Furniture (Cubes)	$2 000	250	$500 000
	Wiring for PC's and Cubes	$120	250	$30 000
	Security System	$75 000	1	$75 000
	Reception Area	$20 000	1	$20 000
	Cafeteria	$20 000	1	$20 000
	PC Installation	$50	250	$12 500
	Data roomsetup	$3 000	1	$3 000

				$1 659 619

	Level 3 - Actual Results

				Year 0	Year 1	Year 2	Year 3	Year 4	Year 5
			Total CapEx	$-	$-	$-	$-	$-	$-

## Project Expenses
Business Case Spreadsheet (Template)
	Project Expenses
					External Project Expenses (Fees & Other Expenses)					Internal Project Expenses (Personnel & Other Expenses)
	Level 1 - High Level Estimates

			Assumptions	Year 0	Year 1	Year 2	Year 3	Year 4	Year 5					Year 0	Year 1	Year 2	Year 3	Year 4	Year 5
	External Project Expenses (Fees & Other Expenses)			$-	$-	$-	$-	$-	$-			Internal Project Expenses (Personnel & Other Expenses)			$-	$-	$-	$-	$-	$-

	Level 2 - Parametric Estimates
			Assumptions	Year 0	Year 1	Year 2	Year 3	Year 4	Year 5					Assumptions	Year 0	Year 1	Year 2	Year 3	Year 4	Year 5
	External Project Expenses (Fees & Other Expenses)			$621 575					Internal Project Expenses (Personnel & Other Expenses)			$582 981
	External Fees Contingency		15%	$81 075					Internal Project Costs Contingency		15%	$76 041					Personnel
	Travel & Expenses		15%	$70 500					Travel & Expenses		5%	$24 140					Travel
	Integrator Fees	(Daily Rate)	$1 000	$470 000					Internal Labor Cost	(Daily Cost)	$340	$482 800					Personnel
					Corresponding Government Cost Categories
					(From OMB Circular No. 76: Revised Supplemental Handbook, Performance of Commercial Activities
				Project Work Breakdown Structure (WBS) for
					Generic IT Project

			Participants	# Occurrences		Estimating Factor	Duration (Days)	FTEs	% External	Integrator FTEs	Client FTEs
	Project Name
	Phase I					1890,0		470,0	1420,0

	Workstream 1					1220,0		210,0	1010,0
	Task Package 1
		Task 1	4	3		Meetings	10	120,0	50%	60,0	60,0
		Task 2	2	5		Tables	20	200,0	0%	0,0	200,0
		Task 3
	Task Package 2
		Task 1	4	3		Meetings	25	300,0	50%	150,0	150,0
		Task 2	2	5		Tables	60	600,0	0%	0,0	600,0

	Workstream 2					670,0		260,0	410,0
	Task Package 1
		Task 1	4	3		Meetings	10	120,0	50%	60,0	60,0
		Task 2	2	5		Tables	35	350,0	0%	0,0	350,0
		Task 3	2	5		Sessions	20	200,0	100%	200,0	0,0

	Level 3 - Actual Results

			Assumptions	Year 0	Year 1	Year 2	Year 3	Year 4	Year 5					Year 0	Year 1	Year 2	Year 3	Year 4	Year 5
	External Project Expenses (Fees & Other Expenses)			$-	$-	$-	$-	$-	$-			Internal Project Expenses (Personnel & Other Expenses)			$-	$-	$-	$-	$-	$-

## Incrtl Ongoing Costs
Business Case Spreadsheet (Template)
	Incremental Ongoing Costs

	Level 1 - High Level Estimates

	Incremental Commissions & Cost of Sales	Estimated as percentage of revenues from prior operating financial data.
	- used in row 10 of CostBenefit Summary tab
		Year 0	Year 1	Year 2	Year 3	Year 4	Year 5
	Estimate: Commissions & Cost of Sales	0%	15%	15%	15%	15%	15%

		Description of supporting research and data source(s):

	Incremental Cost of Operations
	- used in row 11 of CostBenefit Summary tab

		Estimated as percentage of revenues from prior operating financial data.
		Year 0	Year 1	Year 2	Year 3	Year 4	Year 5
	Estimate: Cost of Operations	0%	40%	40%	40%	40%	40%

		Description of supporting research and data source(s):

	Incremental SG&A Cost
	- used in row 12 of CostBenefit Summary tab

		Estimated as percentage of revenues from prior operating financial data.
		Year 0	Year 1	Year 2	Year 3	Year 4	Year 5
	Estimate: SG&A Cost	0%	10%	10%	10%	10%	10%

		Description of supporting research and data source(s):

	Level 2 - Parametric Estimates

	Incremental Commissions & Cost of Sales
	- used in row 10 of CostBenefit Summary tab		(Insert parametric estimates of Commissions & Cost of Sales sub-categories in this space.)

		Year 0	Year 1	Year 2	Year 3	Year 4	Year 5
	Total Commissions & Cost of Sales	$-	$-	$-	$-	$-	$-
	(Insert calculations in row above to sum sub-categories of parametric estimates of ongoing Commissions & Cost of Sales from rows in Level 2 section above.)

	Incremental Cost of Operations		(Sample) Ongoing Operating Costs of a Call Center
	- used in row 11 of CostBenefit Summary tab

		Year 0	Year 1	Year 2	Year 3	Year 4	Year 5
	Total Annual Cost of Operations	$-	$15 037 991	$13 770 359	$13 770 359	$13 770 359	$13 770 359

					# Sites
	Variables			Administrative Seats		34		1,00
	Center Size (seats)	250		Training Seats		41
	Sq. Ft. (120 per seat)	30000		Agent Seats	70%	175
	Turnover % - Annual	60%				250
	Benefits loading factor	24%		Operating Cost/Seat			Annual Operating Costs Per Site
				$52 521			Variable - Year one	$13 130 291
				47 450,64			Variable - Out years	$11 862 659
				7 630,80			Fixed - Every year	$1 907 700

	Year One Operating Costs					Out Years Operating Costs					Corresponding Government Cost Categories
		Headcount	Salary/ Cost per unit	Total Loaded Cost				Headcount	Salary/ Cost per unit	Total Loaded Cost		(From OMB Circular No. 76: Revised Supplemental Handbook, Performance of Commercial Activities
	Variable based on headcount					Variable based on headcount					Personnel
	Center Director	1	$70 000	$86 800			Center Director	1	$70 000	$86 800		Personnel
	Managers	2	$57 324	$142 164	100	ratio	Managers	2	$57 324	$142 164		Personnel
	Supervisors	11	$32 913	$446 383	20	ratio	Supervisors	11	$32 913	$446 383		Personnel
	Leads	9	$28 198	$314 690	25	ratio	Leads	9	$28 198	$314 690		Personnel
	Agents	219	$19 608	$5 318 670	$9,50		Agents	219	$19 608	$5 318 670		Personnel
	Tech Support	1	$55 000	$68 200			Tech Support	1	$55 000	$68 200		Personnel
	Facility Manager	1	$35 000	$43 400			Facility Manager	1	$35 000	$43 400		Personnel
	Workforce coordinator	3	$20 640	$76 781			Workforce coordinator	3	$20 640	$76 781		Personnel
	Admin	2	$20 640	$51 187			Admin	2	$20 640	$51 187		Personnel
	HR Coordinator	2	$32 913	$81 624			HR Coordinator	2	$32 913	$81 624		Personnel
	Trainers	2	$32 913	$81 624			Trainers	2	$32 913	$81 624		Personnel

	Initial Recruiting	253	$1 500	$379 031			Initial Recruiting	0	$1 500	$-		Personnel
	Initial Hiring	253	$2 000	$505 375			Initial Hiring	0	$2 000	$-		Personnel
	Initial Training	253	$1 200	$303 225			Initial Training	0	$1 200	$-		Personnel
	Recruiting for Churn	131	$1 500	$196 875			Recruiting to cover churn	131	$1 500	$196 875		Personnel
	Churn Hiring Fees	131	$2 000	$262 500			Churn Hiring Fees	131	$2 000	$262 500		Personnel
	Churn Training Cost	131	$1 200	$157 500			Churn Training Cost	131	$1 200	$157 500		Personnel

	Vacation Exp.	253	$2 400	$606 450			Vacation Exp.	253	$2 400	$606 450		Personnel
	Bonus Exp.	253	$1 300	$328 494			Bonus Exp.	253	$1 300	$328 494		Personnel
	Service awards	253	$100	$25 269			Service awards	253	$100	$25 269		Personnel
	Incent. Pay	253	$275	$69 489			Incent. Pay	253	$275	$69 489		Personnel

	Unemployment taxes	253	$1 100	$277 956			Unemployment taxes	253	$1 100	$277 956		Personnel
	Payroll taxes	253	$3 000	$758 063			Payroll taxes	253	$3 000	$758 063		Personnel
	Grp. Medical Ins.	253	$4 200	$1 061 288			Grp. Medical Ins.	253	$4 200	$1 061 288		Personnel
	Pens. Plan contrib..	253	$480	$121 290			Pens. Plan contrib..	253	$480	$121 290		Personnel
	401K Contrib..	253	$4 050	$1 023 384			401K Contrib..	253	$4 050	$1 023 384		Personnel
	Sick pay exp.	253	$410	$103 602			Sick pay exp.	253	$410	$103 602		Personnel
	Other EE Benefits	253	$-	$-			Other EE Benefits	253	$-	$-		Personnel
	Seminars and classes	253	$-	$-			Seminars and classes	253	$-	$-		Personnel
	Educational Reimb.	253	$410	$103 602			Educational Reimb.	253	$410	$103 602		Personnel
	Other pers. Exp.	253	$140	$35 376			Other pers. Exp.	253	$140	$35 376		Personnel

	Temp Help Days	500	$200	$100 000	$ 25.00 / hour		Temp Help Days	100	$200	$20 000		Personnel

	Total			$13 130 291			Total			$11 862 659

					Fixed Annual costs - every year
					Travel and entertainment					Travel
					Lodging	24	$200	$4 800		Travel
					Airfare	8	$800	$6 400		Travel
					Rent Cars	0	$-	$-		Travel
					Other	253	$-	$-		Travel
					Meals	24	$50	$1 200		Travel
					Meals-entertainment	24	$50	$1 200		Travel
					Meetings	3	$5 000	$15 000		Travel
					Postage	253	$75	$18 952		Materials & Supply Costs
					Office supplies	253	$75	$18 952		Materials & Supply Costs
					Stationary/forms	253	$0,50	$126		Materials & Supply Costs
					Office eq.	1	$288 000	$288 000		Materials & Supply Costs
					Rent- office eq.	1	$84 000	$84 000		Materials & Supply Costs
					Depreciation of PC's	1	$80 340	$80 340		Depreciation
					Depreciation of Furniture	1	$61 956	$61 956		Depreciation
					Computer supplies	253	$20	$5 054		Materials & Supply Costs
					Hardware maintenance	1	$49 116	$49 116		Maintenance & Repair
					Software maintenance	1	$24 567	$24 567		Maintenance & Repair
					Bank charges	1	$1 000	$1 000		Other Costs
					Dues/subscriptions	253	$14	$3 538		Other Costs

					Facilities - rent	30000	$22	$660 000		Rent
					Utilities	30000	$9,50	$285 000		Utilities
					Facil. Repair	30000	$4,20	$126 000		Maintenance & Repair
					Other Occ. Exp.	30000	$5,75	$172 500		Insurance

					Total			$1 907 700

	Incremental SG&A Cost
	- used in row 12 of CostBenefit Summary tab
			(Insert parametric estimates of SG&A Cost sub-categories in this space.)

		Year 0	Year 1	Year 2	Year 3	Year 4	Year 5
	Total Annual SG&A Costs	$-	$-	$-	$-	$-	$-
	(Insert calculations in row above to sum sub-categories of parametric estimates of ongoing SG&A from rows in Level 2 section above.)

	Level 3 - Actual Results

	Incremental Commissions & Cost of Sales
	- used in row 10 of CostBenefit Summary tab
			(Insert quantification of actual Commissions & Cost of Sales sub-categories in this space.)

		Year 0	Year 1	Year 2	Year 3	Year 4	Year 5
	Total Annual Commissions & Cost of Sales	$-	$-	$-	$-	$-	$-
	(Insert calculations in row above to sum sub-categories of actual ongoing Commissions & Cost of Sales from rows in Level 3 section above.)

	Incremental Cost of Operations
	- used in row 11 of CostBenefit Summary tab
			(Insert quantification of actual Cost of Operations sub-categories in this space.)

		Year 0	Year 1	Year 2	Year 3	Year 4	Year 5
	Total Annual Cost of Operations	$-	$-	$-	$-	$-	$-
	(Insert calculations in row above to sum sub-categories of actual ongoing Cost of Operations from rows in Level 3 section above.)

	Incremental SG&A Cost
	- used in row 12 of CostBenefit Summary tab
			(Insert quantification of actual SG&A sub-categories in this space.)

		Year 0	Year 1	Year 2	Year 3	Year 4	Year 5
	Total Annual SG&A Costs	$-	$-	$-	$-	$-	$-
	(Insert calculations in row above to sum sub-categories of actual ongoing SG&A from rows in Level 3 section above.)

## Savings
Business Case Spreadsheet (Template)
	Savings Benefit Estimates

	Level 1 - High Level Estimates
			Year 0	Year 1	Year 2	Year 3	Year 4	Year 5

				(Insert high level cost savings sub-category estimates in this space.)

		Grand Total Cost Savings	$-	$-	$-	$-	$-	$-
			(Insert calculations in row bove to sum sub-categories of high-level savings from rows in Level 1 section above.)

	Level 2 - Parametric Estimates

	Dept.	Description	Units	YR 1	YR 2	YR 3	YR 4	YR 5	Total Improvement
	Purchasing
		Improvement in efficiency of personnel
		Est. % improvement in Purchasing productivity	10%		10,0%	10,0%	10,0%	10,0%
		Actual annual burdened cost of worker	$40 000		$41 000	$42 025	$43 076	$44 153
		Avg number of workers in dept. using system	10		10	10	10	10
		Annual Cost Savings		$40 000	$41 000	$42 025	$43 076	$44 153	$210 253
		Better visibility of purchased product quality
		Avg. annual number of purchase orders	1 000		1 000	1 000	1 000	1 000
		Avg. P.O. amount	$50 000		$51 250	$52 531	$53 845	$55 191
		Est. incremental % of comparable products identified	10%		10%	10%	10%	10%
		Est. % improvement in price per P.O.	10%		10%	10%	10%	10%
		Annual Cost Savings		$500 000	$512 500	$525 313	$538 445	$551 906	$2 628 164
		Better visibility of same vendor purchases
		Avg. annual number of purchase orders	1 000		$1 000	$1 000	$1 000	$1 000
		Avg. P.O. amount	$50 000		$51 250	$52 531	$50 000	$50 000
		Est. incremental % of same vendor/same month orders	10%		10%	10%	10%	10%
		Est. % improvement in volume discount	15%		15%	15%	15%	15%
		Annual Cost Savings		$750 000	$768 750	$787 969	$750 000	$750 000	$3 806 719
		Total Purchasing		$1 290 000	$1 322 250	$1 355 306	$1 331 521	$1 346 059	$6 645 136
	Maintenance & Repair
		Improvement in efficiency of personnel
		Est. improvement in Maintenance & Repair worker productivity	10%		10,0%	10,0%	10,0%	10,0%
		Actual annual burdened cost of worker	$40 000		$41 000	$42 025	$43 076	$44 153
		Avg number of workers in dept. using system	10		10	10	10	10
		Annual Cost Savings		$40 000	$41 000	$42 025	$43 076	$44 153	$210 253
		Placeholder
		Actual	0		-	-	-	-
		Actual	10		10	10	10	10
		Estimate	10%		10%	10%	10%	10%
		Actual	$30 000		$30 000	$30 000	$30 000	$30 000
		Annual Cost Savings		$-	$-	$-	$-	$-	$-
		Total Maintenance & Repair		$40 000	$41 000	$42 025	$43 076	$44 153	$210 253
	Warehousing/Inventory Control
		Improvement in efficiency of personnel
		Est. improvement in warehouse/inventory worker productivity	10%		10,0%	10,0%	10,0%	10,0%
		Actual annual burdened cost of worker	$40 000		$41 000	$42 025	$43 076	$44 153
		Actual number of workers in dept. using system	10		10	10	10	10
		Annual Cost Savings		$40 000	$41 000	$42 025	$43 076	$44 153	$210 253
		Reduced Carrying Costs
		Est. avg. reduction in # parts per warehouse	10%		10,0%	10,0%	10,0%	10,0%
		Avg # parts per warehouse	$10 000		10 000	10 000	10 000	10 000
		Actual # warehouses	3		3	3	3	3
		Avg annual carrying cost per part	$25,43		$26,07	$26,72	$27,39	$28,07
		Annual Cost Savings		$76 290	$78 197	$80 152	$82 156	$84 210	$401 005
		Total Warehousing		$116 290	$119 197	$122 177	$125 232	$128 362	$611 258
	Logistics/ Shipping/ Receiving
		Improvement in efficiency of personnel
		Est. improvement in Logistics worker productivity	10%		10,0%	10,0%	10,0%	10,0%
		Actual annual burdened cost of worker	$40 000		$41 000	$42 025	$43 076	$44 153
		Avg number of workers in dept. using system	10		10	10	10	10
		Annual Cost Savings		$40 000	$41 000	$42 025	$43 076	$44 153	$210 253
		Improvement in non-labor cost of work order handling
		Actual avg non-labor cost per work order	$54,29		$55,65	$57,04	$58,46	$59,93
		Est. avg. reduction in cost per work order	20%		20,0%	20,0%	20,0%	20,0%
		Actual annual number of work orders	4 500		$4 500	$4 500	$4 500	$4 500
		Annual Cost Savings		$48 861	$50 083	$51 335	$52 618	$53 933	$256 829
		Reduce Premium Freight
		Avg annual shipments	10 000		10 000	10 000	10 000	10 000
		Actual avg. cost per premium shipment	$50,00		$51,25	$52,53	$53,84	$55,19
		Actual % of premium freight shipments	10%		10%	10%	10%	10%
		Estimated reduction in premium freight shipments	25%		25%	25%	25%	25%
		Annual Cost Savings		$12 500	$12 813	$13 133	$13 461	$13 798	$65 704
		Total Distribution		$101 361	$103 895	$106 492	$109 155	$111 884	$532 787
	Customer Service & Order Mgt.
		Improvement in efficiency of personnel
		Est. avg improvement in C.S. & O.M. worker productivity	10%		10,0%	10,0%	10,0%	10,0%
		Actual annual burdened cost of worker	$40 000		$41 000	$42 025	$43 076	$44 153
		Avg annual number of workers in dept. using system	10		10	10	10	10
		Annual Cost Savings		$40 000	$41 000	$42 025	$43 076	$44 153	$210 253
		Increased accuracy of orders
		Actual avg annual # customer orders	2 200		2 200	2 200	2 200	2 200
		Avg annual % of orders that are incorrect	10%		10,0%	10,0%	10,0%	10,0%
		Est. % reduction of incorrect orders	50%		50%	50%	50%	50%
		Actual % returns of incorrect orders	85%		85%	85%	85%	85%
		Avg cost to re-stock returns	$300		$308	$315	$323	$331
		Annual Cost Savings		$28 050	$28 751	$29 470	$30 207	$30 962	$147 440
		Decreased customer complaint calls
		Actual avg annual # customer complaint calls	5 000		5 000	5 000	5 000	5 000
		Est. % reduction in complaint calls	50%		50%	50%	50%	50%
		Avg cost per complaint call	$25		$25,63	$26,27	$26,92	$27,60
		Annual Cost Savings		$62 500	$64 063	$65 664	$67 306	$68 988	$328 521
		Total Customer Service / Admin.		$130 550	$133 814	$137 159	$140 588	$144 103	$686 214
	Information Systems
		Improvement in efficiency of personnel
		Est. avg improvement in IS worker productivity	10%		10,0%	10,0%	10,0%	10,0%
		Actual avg burdened cost of worker	$40 000		$41 000	$42 025	$43 076	$44 153
		Avg annual number of workers in dept. using system	10		10	10	10	10
		Annual Cost Savings		$40 000	$41 000	$42 025	$43 076	$44 153	$210 253
		Reduction in maintenance costs (consolidation)
		Est. # decommissioned systems	3		3	3	3	3
		Actual annual cost of software maintenance contracts per system	$10 000		10 250	10 506	10 769	11 038
		Actual annual cost of hardware maintenance contracts per system	$30 000		$30 750	$31 519	$32 307	$33 114
		Annual Cost Savings		$120 000	$123 000	$126 075	$129 227	$132 458	$630 759
		Total Information Systems		$160 000	$164 000	$168 100	$172 303	$176 610	$841 013
	Finance/ Accounting
		Improvement in efficiency of personnel
		Est. avg improvement in Finance worker productivity	10%		10,0%	10,0%	10,0%	10,0%
		Actual annual burdened cost of worker	$40 000		$41 000	$42 025	$43 076	$44 153
		Avg annual number of workers in dept. using system	10		10	10	10	10
		Annual Cost Savings		$40 000	$41 000	$42 025	$43 076	$44 153	$210 253
		Placeholder
		Actual	0		-	-	-	-
		Actual	10		10	10	10	10
		Estimate	10%		0%	0%	0%	0%
		Actual	$30 000		$30 000	$30 000	$30 000	$30 000
		Annual Cost Savings		$-	$-	$-	$-	$-	$-
		Total Finance & Accounting		$40 000	$41 000	$42 025	$43 076	$44 153	$210 253
	Human Resources
		Improvement in efficiency of personnel
		Est. avg improvement in HR worker productivity	10%		10,0%	10,0%	10,0%	10,0%
		Actual annual burdened cost of worker	$40 000		$41 000	$42 025	$43 076	$44 153
		Avg annual number of workers in dept. using system	10		10	10	10	10
		Annual Cost Savings		$40 000	$41 000	$42 025	$43 076	$44 153	$210 253
		Placeholder
		Actual	0		-	-	-	-
		Actual	10		10	10	10	10
		Estimate	10%		0%	0%	0%	0%
		Actual	$30 000		$30 000	$30 000	$30 000	$30 000
		Annual Cost Savings		$-	$-	$-	$-	$-	$-
		Total Human Resources		$40 000	$41 000	$42 025	$43 076	$44 153	$210 253
			Year 0	Year 1	Year 2	Year 3	Year 4	Year 5
		Grand Total Cost Savings		$1 918 201	$1 966 156	$2 015 310	$2 008 025	$2 039 475	$9 947 167

	Level 3 - Actual Results

			Year 0	Year 1	Year 2	Year 3	Year 4	Year 5

					(Insert actual cost savings sub-category quantification in this space.)

		Grand Total Cost Savings	$-	$-	$-	$-	$-	$-
			(Insert calculations in row bove to sum sub-categories of actual savings from rows in Level 3 section above.)

## Revenue
Business Case Spreadsheet (Template)
	Revenue Benefit Estimates

	Level 1 - High Level Estimates
			Year 0	Year 1	Year 2	Year 3	Year 4	Year 5

					(Insert high level revenue sub-category estimates in this space.)

		Grand Total Incremental Revenue	$-	$-	$-	$-	$-	$-
			(Insert calculations in row above to sum sub-categories of high-level revenue estimates from rows in Level 1 section above.)

	Level 2 - Parametric Estimates

	Dept.	Description	Units	YR 1 Increased Revenues	YR 2 Increased Revenues	YR 3 Increased Revenues	YR 4 Increased Revenues	YR 5 Increased Revenues	Total Improvement
	Sales & Marketing
	1	Increased revenue per order
	1a	Avg. annual customer orders	2 200		2 200	2 200	2 200	2 200		checked
		Actual price per order	$2 000		$2 100	$2 205	$2 315	$2 431		checked
	1b	Est. % increase in price per order	5%		5,0%	5,0%	5,0%	5,0%		checked
		Annual Revenue Increase		$220 000	$231 000	$242 550	$254 678	$267 411	$1 215 639	checked
	2	Improved close rate
	2a	Avg annual # of customer orders	2 200		2 200	2 200	2 200	2 200		checked
	2b	Customer order price	$2 000		$2 100	$2 205	$2 315	$2 431		checked
	2c	Avg annual close rate	72%		72%	72%	72%	72%		checked
	2d	Est. % improvement in close rate	10%		10%	10%	10%	10%		checked
		Annual Revenue Increase		$316 800	$332 640	$349 272	$366 736	$385 072	$1 750 520	checked
	3	Shortened processing time for orders		Annual Est. Change
	3a	Annual customer orders	2 200		2 420	2 541	2 605	2 637		checked
	3b	Customer order price	$2 000		$2 100	$2 205	$2 315	$2 431		checked
	3d	Est. % decrease in order processing time	10%	50%	5,0%	2,5%	1,3%	0,6%		checked
	3e	Resulting incremental customer orders	220		121	64	33	16		checked
		Annual Revenue Increase		$440 000	$254 100	$140 073	$75 377	$40 067	$949 617	checked
	4	Better efficiency for personnel who travel		Annual Est. Change
	4a	Est. % improvement in sales travel efficiency	10%	50%	5%	3%	1%	1%		checked
	4b	Avg annual sales per rep	$440 000		484 000	508 200	520 905	527 416		checked
	4c	Avg annual number of reps	10		10	10	10	10		checked
		Annual Revenue Increase		$440 000	$242 000	$127 050	$65 113	$32 964	$907 127	checked
	5	Increase in Customer Retention
	5a	Avg annual # of customers	500		500	500	500	500		checked
	5b	Average customer loss per year	5%		5,0%	5,0%	5,0%	5,0%		checked
	5c	Average annual revenue per existing customer	$8 800		$8 800	$8 800	$8 800	$8 800		checked
	5d	Est avg annual reduction in customer loss	10%		10,0%	10,0%	10,0%	10,0%		checked
		Annual Revenue Increase		$22 000	$22 000	$22 000	$22 000	$22 000	$110 000	checked
	6	Total Sales & Marketing		$1 438 800	$1 081 740	$880 945	$783 903	$747 515	$4 932 902	checked
	Customer Service & Order Mgt.
	6	Improvement in market share due to customer satisfaction		Annual Est. Change
		# of existing customers	500		523	521	508	488		checked
	6a	Est. % improvement in customer satisfaction	10%	50%	5,0%	2,5%	1,3%	0,6%		checked
	6b	Avg annual incremental customers	50		26	13	6	3		checked
	6c	Average annual revenue per existing customer	$8 800		8 800	8 800	8 800	8 800		checked
		Annual Revenue Increase		$440 000	$229 900	$114 663	$55 826	$26 849	$867 238	checked
	7	Incremental Sales Leads passed by Customer Service
		Actual leads passed per C.S. worker	150		165	182	200	220		checked
	7a	Est. incremental % of leads passed per C.S. worker	10%		10%	10%	10%	10%		checked
	7b	Avg annual C.S. workers using new system	10		10	10	10	10		checked
	7c	Avg annual % leads that turn into deals	10%		10%	10%	10%	10%		checked
	7d	Average customer order size	2 000		$2 000	$2 000	$2 000	$2 000		checked
		Annual Revenue Increase		$30 000	$33 000	$36 300	$39 930	$43 923	$183 153	checked
	8	Total Customer Service / Admin.		$470 001	$262 900	$150 963	$95 756	$70 772	$1 050 391	checked
			Year 0	Year 1	Year 2	Year 3	Year 4	Year 5
		Grand Total Benefit Sales, Mktg., C.S. & Admin.		$1 908 801	$1 344 640	$1 031 907	$879 659	$818 287	$5 983 294

	Level 3 - Actual Results
	Dept.	Description	Units	YR 1 Increased Revenues	YR 2 Increased Revenues	YR 3 Increased Revenues	YR 4 Increased Revenues	YR 5 Increased Revenues	Total Improvement

				(Insert actual revenue sub-category quantifications in this space.)

		Grand Total Incremental Revenue	$-	$-	$-	$-	$-	$-
			(Insert calculations in row above to sum sub-categories of actual revenue quantification from rows in Level 3 section above.)

## BenefitsID
Business Case Spreadsheet (Template)
	Sample Benefits Identification Model					Benefit Calculations

				Financial Levers				Operational Levers			Critical Success Factors	Key Performance Indicators (KPIs)	Sales & Marketing	Purchasing	Maintenance & Repair	Warehousing/Inventory Control	Logistics/ Shipping/ Receiving	Customer Service & Order Mgt.	Information Systems	Finance/ Accounting	HR
					Increase price		•Profit-driven sales efforts: / – Offer “right” mix / – Improve tactical pricing management
					Increase revenues		Increase volume
				Increase gross / profit				Improve mix				# of lost customers
					Improve process		• Optimal manufacturing processes / • Most profitable capacity allocation/utilization
		Increase net operating / profit after tax (NOPAT) / (I/S)				Decrease manufacturing / costs		Reduce cost of materials
					Avg cost per same size P.O.
					Improve plant utilization
					Reduce / selling costs			Increase productivity
					Decrease staffing		• Focus on high-profit accounts / • Reduced sales management layers
				Decrease operating / expenses				Optimize scheduling
					Reduce / distribution costs					• Improved inventory flow visibility / – Lower transportation costs / – Higher facilities utilization / – Less “firefighting”, more accurate planning / •Better carrier evaluation /mgmt.		# days to fill an avg order
					Optimize physical network / Decrease staffing				# returns
					$ per work order
	Enterprise-Wide / Value Creation					Lower Customer Service & / Administration Costs / Use alternative distribution		• Improved Customer Service access to information / – More consistent service / – Faster problem resolution / – Lower C.S. cost / • Improved Admin. access to information / - Significantly lower G&A "overhead"		Avg $ of premium frieght cost/order
					Reduce / administrative costs					# of complaint calls

					Lower I/S costs / Lower Finance/Acctg. costs				# IS personnel					($/FTE) x FTEs saved = Reduction in labor
					Reduce / R&D		Lower HR costs				$ annual maintenance contract cost					($/system/maintenance agt.) x systems consolidated = Reduction in maintenance contract cost
					Improve capital planning/ investment process
				Capital / deployment					• Improved Supply Chain visibility
					Reduce inventories			– Improved order fill rates	Avg days for order fill
		Improve capital allocation / (B/S)					Reduce A/P increase A/R			•Improved capital stewardship / – Increased capital productivity / – Reduced inventory investment & carrying costs / – Reduced receivables investment	% of orders filled in less than 1 day

				Cost of / capital				N/A

## Glossary
Business Case Spreadsheet (Template)
	Glossary

		Method/Metric	Definition/Brief Description	Use
		Net Present Value (NPV)	is the sum of the discounted (at the cost of capital) cash flows of the project.	To compare projects using a common cost of capital or discount rate. NPV does not explicitly reflect the uncertainty of the cash flow forecasts.
		Internal Rate of Return (IRR)	is the discount rate, which when applied to the cash flows of the project produces a NPV equal to zero.	IRR provides a uniform measure for evaluating different projects. It is a special case of NPV.
		Payback Period (aka Breakeven)	is the length of time required for the sum of the net cash flows of the project to equal zero.	Used to compare projects in terms of time to produce positive nominal results. Many organizations will not undertake projects which take longer than x years to "pay for themselves"
		Parameter	is an estimate or assumption provided as input.	Allows user to tailor the business case template to the specific project at hand.
		tornado diagram	is a set of calculations and a chart summarizing the relative influence of various parameters on the defined output cell.	Provides preliminary analysis of the sensitivity or relative strength of influence of a parameter provided in 3 point (Minimum, Best Estimate, Maximum) range. Allows easy visualization of parameters that carry the most influence in a model's outcome. In the Business Case Template, NPV is typically used as the best measure of BCT outcome.